## Overview
BOZ Jewelry Retail and E-commerce Transformation
Status | Delivered
Domain | Retail and e-commerce
Role | IT Project Manager, E-commerce and Digital Systems
Business problem | Fragmented delivery updates, repetitive customer enquiries and inconsistent custom-order requirement capture reduced visibility and created friction in the customer journey.
Measure | Value | Source
Business requirements | 5 | Requirements
Must requirements | 4 | Requirements
Should requirements | 1 | Requirements
Functional requirements | 6 | Functional
Requirements with a test | 5 | Traceability
Tests with status "Passed" | 5 | UAT
High risks | 3 | RAID
Stakeholder groups | 5 | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Create clear ownership and delivery visibility
OBJ-02 | Improve customer support and custom-order journeys
OBJ-03 | Support Microsoft 365 adoption and controlled collaboration
OBJ-04 | Validate changes and measure post-implementation value

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Leadership can view project status, ownership and blockers in one place | Must | OBJ-01 | Create clear ownership and delivery visibility | Every active item shows owner, status, due date and dependency
BR-02 | Authorised colleagues can access controlled shared information | Must | OBJ-03 | Support Microsoft 365 adoption and controlled collaboration | Current documents are accessible according to role; unauthorised access is denied
BR-03 | Customers receive consistent answers to common questions | Should | OBJ-02 | Improve customer support and custom-order journeys | An approved answer is returned, or the query is escalated to a person
BR-04 | Custom-order specifications are confirmed before fulfilment | Must | OBJ-02 | Improve customer support and custom-order journeys | Required details and customer confirmation are recorded before production starts
BR-05 | Changes are tested with business users before release | Must | OBJ-04 | Validate changes and measure post-implementation value | Agreed scenarios pass and exceptions are logged and retested

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Delivery board holds one item per workstream task with owner, status, due date and dependency fields | Status values: Not started, In progress, Blocked, Done
FR-02 | BR-01 | Weekly status summary is generated automatically for leadership | Summary lists blocked and overdue items first
FR-03 | BR-02 | Microsoft 365 groups control access to shared libraries by role | New users are added to a role group, never to individual files
FR-04 | BR-03 | Chatbot returns approved answers for common product, delivery and returns questions | Unmatched or sales-intent queries route to customer service
FR-05 | BR-04 | Custom-order form captures metal, size, stones, engraving, budget and reference images | Order cannot move to production until customer confirmation is recorded
FR-06 | BR-05 | Test scenarios are linked to requirement IDs with pass or fail and defect reference | A release needs all Must scenarios passed

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-04 | customer ordering a custom piece | to confirm my specification before it is made | what I receive matches what I asked for | I have submitted a custom request | I review the summary and confirm it | the order moves to production with my confirmed brief attached
US-02 | BR-03 | customer with a routine question | an instant, accurate answer | I do not wait in a manual queue | my question matches an approved topic | I ask it on the website or WhatsApp | the approved answer is returned, or I am passed to a person
US-03 | BR-01 | business owner | one view of every workstream | I can see blockers without chasing people | items are on the delivery board | I open the weekly summary | blocked and overdue items appear first with their owners

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Business owner | High | High | Commercial value, cost and risk | Milestones, options, decisions, benefits | Decision-focused review | Weekly | Manage closely
Customer-service team | Medium | High | Usability and workload | Process changes, escalation routes | Demonstration and feedback session | Before each release | Keep informed
Developers | High | High | Feasible, testable scope | Workflows, data, acceptance criteria | Requirements walkthrough and backlog | Each sprint | Manage closely
Creatives | Medium | Medium | Brand and content dependencies | Priorities, asset deadlines | Visual brief and checkpoint | Per asset batch | Monitor
Customers | Low | High | Clear, reliable journey | Product, order and support information | Usability checks and feedback | At launch and post-launch | Keep informed

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Users revert to fragmented communication | Medium | Demonstrations and one agreed channel per purpose | Business owner
R-02 | Custom requirements are misunderstood | High | Structured capture and customer confirmation | Customer service lead
R-03 | Automated answers become inaccurate | High | Approved content and escalation route | Customer service lead
R-04 | Permissions expose information incorrectly | High | Role-group access and access tests | IT project manager

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | items exist on the delivery board | the owner opens the weekly summary | blocked and overdue items show owner, due date and dependency | Passed
UAT-02 | BR-02 | a colleague without the finance role | they open the finance library | access is denied and the attempt is logged | Passed
UAT-03 | BR-03 | a customer asks a delivery-time question | the chatbot receives it | the approved answer is returned | Passed
UAT-04 | BR-04 | a custom request without confirmation | staff try to move it to production | the move is blocked until confirmation is recorded | Passed
UAT-05 | BR-05 | release candidate is ready | the scenario pack is run with business users | all Must scenarios pass and exceptions are logged | Passed

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 | OBJ-01 | FR-01, FR-02 | US-03 | UAT-01 | 1
BR-02 | OBJ-03 | FR-03 | None | UAT-02 | 1
BR-03 | OBJ-02 | FR-04 | US-02 | UAT-03 | 1
BR-04 | OBJ-02 | FR-05 | US-01 | UAT-04 | 1
BR-05 | OBJ-04 | FR-06 | None | UAT-05 | 1

## Data Dictionary
Field | Type | Definition | Allowed values
work_item_id | Text | Unique delivery item | WI-0001 format
owner | Text | Responsible person or team | Named role
status | Category | Current delivery state | Not started, In progress, Blocked, Done
request_type | Category | Type of customer contact | Routine question, Sales lead, Custom order, Complaint
custom_specification | Text | Confirmed custom-order details | Structured form fields
confirmed_at | Datetime | Customer confirmation time | ISO 8601