## Overview
Creatrix Empire Marketing Operations and Performance Analysis
Status | Delivered
Domain | Digital marketing, media and entertainment
Role | Digital Marketing Analyst and Delivery Lead
Business problem | Client and internal-brand campaigns needed clearer specialist ownership, cleaner hand-offs and optimisation based on consistent evidence rather than reach alone.
Measure | Value | Source
Business requirements | 4 | Requirements
Must requirements | 3 | Requirements
Should requirements | 1 | Requirements
Functional requirements | 4 | Functional
Requirements with a test | 4 | Traceability
Tests with status "Passed" | 4 | UAT
High risks | 1 | RAID
Stakeholder groups | 5 | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Anchor every campaign to an agreed objective
OBJ-02 | Make specialist ownership and hand-offs visible
OBJ-03 | Consolidate performance evidence
OBJ-04 | Prioritise SEO and channel improvements from evidence

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Every campaign has a clear objective, audience and KPI | Must | OBJ-01 | Anchor every campaign to an agreed objective | Approved brief records objective, audience and target KPI
BR-02 | Specialist ownership and hand-offs are visible | Must | OBJ-02 | Make specialist ownership and hand-offs visible | Each task shows owner, dependency and approval state
BR-03 | Performance measures are consolidated in one report | Must | OBJ-03 | Consolidate performance evidence | Reach, engagement, traffic and conversion reported with one definition set
BR-04 | Insights inform the next campaign cycle | Should | OBJ-04 | Prioritise SEO and channel improvements from evidence | Recommendations and resulting decisions are recorded

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Brief template requires objective, audience, channel mix and KPI | Production cannot start on an unapproved brief
FR-02 | BR-02 | Task board records owner, due date, dependency and approval | Assets move to publishing only after brand check
FR-03 | BR-03 | Campaign report pulls channel metrics into one template | Metric definitions follow the KPI dictionary
FR-04 | BR-04 | Post-campaign review logs recommendations and decisions | Each recommendation cites the metric that supports it

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | client | to approve the objective before assets are made | the work targets the outcome I need | a draft brief exists | I approve it | production tasks are released to the team
US-02 | BR-03 | account lead | one report with consistent metric definitions | I can compare campaigns fairly | a campaign has ended | I open the report | reach, engagement, traffic and conversion show against target

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Clients and business owners | High | High | Outcome and value | Results against objective | Performance report and review call | End of each campaign | Manage closely
Leadership | High | High | Performance and resource decisions | Portfolio results, capacity | Management summary | Monthly | Manage closely
Copywriters | Low | Medium | Message and audience | Brief, deadlines | Brief handover | Per campaign | Monitor
Design and video teams | Low | Medium | Assets and deadlines | Brief, dependencies | Task board and stand-up | Daily during production | Monitor
Social-media managers | Medium | High | Channel execution | Publishing schedule, KPIs | Channel plan | Weekly | Keep informed

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Unclear brief causes rework | High | Brief approval gate | Delivery lead
R-02 | Metrics use inconsistent definitions | Medium | KPI dictionary | Analyst
R-03 | Late assets delay campaign | Medium | Dependency tracking on task board | Delivery lead
R-04 | Optimisation based on reach alone | Medium | Balanced KPI review | Analyst

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a brief without a KPI | the lead tries to release production tasks | release is blocked until the KPI is added | Passed
UAT-02 | BR-02 | an asset awaiting brand check | the social manager opens the publishing queue | the asset is not available to publish | Passed
UAT-03 | BR-03 | a finished campaign | the report is generated | all four measures appear with dictionary definitions | Passed
UAT-04 | BR-04 | a review meeting has ended | the lead records outcomes | each recommendation links to a metric and a decision | Passed

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 | OBJ-01 | FR-01 | US-01 | UAT-01 | 1
BR-02 | OBJ-02 | FR-02 | None | UAT-02 | 1
BR-03 | OBJ-03 | FR-03 | US-02 | UAT-03 | 1
BR-04 | OBJ-04 | FR-04 | None | UAT-04 | 1

## Data Dictionary
Field | Type | Definition | Allowed values
campaign_id | Text | Unique campaign | CMP-0001 format
channel | Category | Delivery channel | Instagram, TikTok, X, YouTube, Website
reach | Integer | Unique accounts reached | 0 or more
engagement | Integer | Recorded interactions | 0 or more
website_sessions | Integer | Attributed visits | 0 or more
conversion | Integer | Defined campaign outcome count | Defined per brief