## Overview
The Ecommerce Boss Event Operations Automation
Status | Delivered across client engagements
Domain | E-commerce, events and digital services
Role | Founder and Lead Business Analyst
Business problem | Disconnected forms, spreadsheets and email exchanges caused duplicate entry, unclear ownership, inconsistent hand-offs and limited status visibility for client events.
Measure | Value | Source
Business requirements | 5 | Requirements
Must requirements | 3 | Requirements
Should requirements | 2 | Requirements
Functional requirements | 5 | Functional
Requirements with a test | 5 | Traceability
Tests with status "Passed" | 5 | UAT
High risks | 3 | RAID
Stakeholder groups | 5 | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Create one central operational record
OBJ-02 | Automate repeat communications
OBJ-03 | Make ownership and exceptions visible
OBJ-04 | Select tools proportionate to client capacity

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Submissions create one central record | Must | OBJ-01 | Create one central operational record | No manual re-entry; each submission has a unique ID
BR-02 | Approved decisions trigger consistent communication | Must | OBJ-02 | Automate repeat communications | Message is sent and record status updates together
BR-03 | Ownership and status are visible for every record | Must | OBJ-03 | Make ownership and exceptions visible | Every active record has an owner and a state
BR-04 | Failed automations are visible and recoverable | Should | OBJ-03 | Make ownership and exceptions visible | Failures enter an exception queue with a reason
BR-05 | Solution option matches client operating capacity | Should | OBJ-04 | Select tools proportionate to client capacity | Option assessment records cost, feasibility and admin effort

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Form submission creates an Airtable record with a unique ID | Duplicate email and event combination is flagged
FR-02 | BR-02 | Status change to Approved triggers the approved template | Template choice depends on record type
FR-03 | BR-03 | Record view shows owner, status and next action | Records without owner appear in an unassigned view
FR-04 | BR-04 | Automation errors write to an exception table with reason and time | Exceptions older than 48 hours are highlighted
FR-05 | BR-05 | Options matrix scores manual, plug-in and automated approaches | Scored on cost, feasibility, data quality and admin effort

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | event operations assistant | submissions to arrive as records automatically | I stop copying data between tools | an applicant submits the form | the submission is received | one record with a unique ID is created
US-02 | BR-04 | client lead | to see failed messages in one place | no applicant is left without a reply | an email step fails | the automation runs | the record appears in the exception queue with the reason

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Event or client lead | High | High | Cost, control and status | Status, exceptions, costs | Status review and options paper | Weekly | Manage closely
Operations team | Medium | High | Usability and exceptions | How-to guides, exception queue | Walkthrough and handover guide | At handover and on change | Keep informed
Applicants and customers | Low | High | Clear communication | Confirmation, decision, next steps | Automated email | At each status change | Keep informed
Developers and providers | Medium | Medium | Integration requirements | Field maps, triggers | Technical brief | Per build cycle | Monitor
Marketing team | Medium | Medium | Audience and campaign data | Registration counts by source | Dashboard view | Weekly during campaign | Monitor

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Duplicate records | High | Unique IDs and duplicate flags | Business analyst
R-02 | Automation sends the wrong message | High | Trigger tests and approved templates | Business analyst
R-03 | Client cannot maintain the solution | Medium | Options assessment and handover guide | Client lead
R-04 | Failures go unnoticed | High | Exception queue and ageing highlight | Operations lead

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a new form submission | the workflow runs | one record with a unique ID is created | Passed
UAT-02 | BR-02 | a vendor record | status changes to Approved | the vendor approval template is sent once and logged | Passed
UAT-03 | BR-03 | a record with no owner | the operations view is opened | it appears in the unassigned view | Passed
UAT-04 | BR-04 | the email step is forced to fail | the automation runs | an exception with reason and time is created | Passed
UAT-05 | BR-05 | three solution options | the matrix is completed with the client | a recommended option with scores is recorded | Passed

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 | OBJ-01 | FR-01 | US-01 | UAT-01 | 1
BR-02 | OBJ-02 | FR-02 | None | UAT-02 | 1
BR-03 | OBJ-03 | FR-03 | None | UAT-03 | 1
BR-04 | OBJ-03 | FR-04 | US-02 | UAT-04 | 1
BR-05 | OBJ-04 | FR-05 | None | UAT-05 | 1

## Data Dictionary
Field | Type | Definition | Allowed values
record_id | Text | Unique workflow record | REC-0001 format
record_type | Category | Submission type | Registration, Vendor, Volunteer, Lead
status | Category | Workflow state | New, In review, Approved, Declined, Closed
owner | Text | Responsible team member | Named person
communication_status | Category | Message state | Pending, Sent, Failed
exception_reason | Text | Why manual action is needed | Free text from automation log