## Overview
Taash Tax Automation Service
Status | Completed
Domain | Tax technology and financial services
Role | Founder and Product Business Analyst
Business problem | Individuals, freelancers and small businesses struggle to identify the right tax route, calculate liability correctly and track filing through to certificate.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Released" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Classify taxpayer and entity type correctly
OBJ-02 | Explain calculations and the evidence behind them
OBJ-03 | Keep tax rules versioned and current
OBJ-04 | Track File, Pay, Confirm and Certificate
OBJ-05 | Protect taxpayers through data security and a human review route

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Identify taxpayer or entity type | Must | OBJ-01 |  | Validated answers route the user to the correct journey
BR-02 | Distinguish business-name (BN) and incorporated-company (RC) routes | Must | OBJ-01 |  | The relevant state or federal journey appears
BR-03 | Capture income, deductions and evidence status | Must | OBJ-02 |  | Required values and evidence flags are retained
BR-04 | Show the rules and values applied in each result | Must | OBJ-02 |  | An itemised explanation is available for review
BR-05 | Version rules by effective date | Must | OBJ-03 |  | Each result records the active rule version
BR-06 | Track File, Pay, Confirm and Certificate stages | Should | OBJ-04 |  | Current stage and next action are visible
BR-07 | Sensitive data is access controlled | Must | OBJ-05 |  | Unauthorised access is rejected and access events are logged
BR-08 | Uncertain or complex cases have an escalation route | Must | OBJ-05 |  | User receives a clear referral or review option
BR-09 | Guidance content is editable without code deployment | Should | OBJ-03 |  | Authorised editor updates and publishes controlled content

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Eligibility questionnaire classifies PAYE, freelancer, BN or RC | Contradictory answers trigger a confirmation question
FR-02 | BR-02 | BN route shows state obligations; RC route shows federal obligations | Route cannot change after filing starts without reset
FR-03 | BR-03 | Income and deduction entries carry an evidence status | Status values: Uploaded, Pending, Not required
FR-04 | BR-04 | Result page itemises each rule, rate and value applied | Every line references a rule ID
FR-05 | BR-05 | Rule tables hold effective-from and effective-to dates | Calculation uses the version active on the tax period end date
FR-06 | BR-06 | Tracker shows File, Pay, Confirm, Certificate with next action | Stage advances only on confirmed evidence
FR-07 | BR-07 | Role-based access to taxpayer records with an access log | Reviewers see only cases assigned to them
FR-08 | BR-08 | Out-of-scope or low-confidence results route to the review queue | User sees a plain-language limitation message
FR-09 | BR-09 | Content editor publishes guidance with an effective date after approval | Unapproved drafts are never shown to users

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | freelancer | to be told which tax route applies to me | I do not file under the wrong category | I answer the eligibility questions | I submit them | I am routed to the freelancer journey with a plain-language reason
US-02 | BR-04 | small business owner | to see how my liability was calculated | I can check it before paying | my calculation is complete | I open the result | each rule, rate and value is listed with its rule version
US-03 | BR-08 | tax reviewer | to see the rule version and evidence for each referred case | I can assess the calculation quickly | a case is referred to me | I open it | rule version, inputs and evidence status are shown together
US-04 | BR-09 | content administrator | to update guidance with an effective date | published information stays controlled | a rule change is approved | I publish the guidance | it goes live on the effective date and the prior version is kept

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Individuals and PAYE users | Low | High | Clear obligations and reliefs | Route, liability, next step | In-app guidance | Each session | Keep informed
Freelancers | Low | High | Income and allowable cost treatment | Deductions, evidence | Guided journey | Each session | Keep informed
Business owners | Medium | High | Correct entity route | BN or RC obligations | Guided journey and checklist | Each filing period | Keep informed
Tax professionals | High | High | Review and rule validation | Rule tables, edge cases | Rule review workshop | Before each rule release | Manage closely
Engineering and content | High | High | Testable, versioned logic | Decision tables, acceptance criteria | Backlog refinement in Jira | Each sprint | Manage closely

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Rules change after implementation | High | Versioned tables with effective dates | Product owner
R-02 | Estimate treated as professional advice | High | Clear scope statement and review route | Product owner
R-03 | Incorrect classification | High | Confirmation questions and review | Business analyst
R-04 | Sensitive data exposure | High | Least privilege and encryption | Engineering lead

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a user with salary and freelance income | they complete the questionnaire | they are asked to confirm their primary route | Released
UAT-02 | BR-02 | a user selects business name | the journey starts | the state route and its evidence list are shown | Released
UAT-03 | BR-02 | a user selects registered company | the journey starts | the federal company route is shown | Released
UAT-04 | BR-03 | a deduction without evidence | the user continues | the entry is flagged Pending | Released
UAT-05 | BR-04 | declared rent where 20% of it is below the ₦500,000 rent-relief cap (DR-06) | relief is calculated | the 20% value is applied and shown in the explanation | Released
UAT-06 | BR-04 | declared rent where 20% of it is above the ₦500,000 rent-relief cap (DR-06) | relief is calculated | the ₦500,000 cap is applied and shown | Released
UAT-07 | BR-05 | a rule changes effective date | a prior result is reopened | it keeps the original rule version | Released
UAT-08 | BR-06 | payment is confirmed | the tracker refreshes | the stage moves to Confirm with the next action | Released
UAT-09 | BR-07 | an unauthorised user | they request a taxpayer record | access is rejected and the event is logged | Released
UAT-10 | BR-08 | an unsupported case | the result is produced | the escalation option and limitation message appear | Released
UAT-11 | BR-09 | a draft guidance update | it is approved with a future effective date | users see it only from that date | Released

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | US-01 | UAT-01
BR-02 |  | FR-02 | None | UAT-02, UAT-03
BR-03 |  | FR-03 | None | UAT-04
BR-04 |  | FR-04 | US-02 | UAT-05, UAT-06
BR-05 |  | FR-05 | None | UAT-07
BR-06 |  | FR-06 | None | UAT-08
BR-07 |  | FR-07 | None | UAT-09
BR-08 |  | FR-08 | US-03 | UAT-10
BR-09 |  | FR-09 | US-04 | UAT-11

## Data Dictionary
Field | Type | Definition | Allowed values
taxpayer_id | Text | Controlled user identifier | Internal ID
taxpayer_type | Category | Classified route | PAYE, Freelancer, BN, RC
income_value | Decimal | Declared income for the period | Naira, 2 dp
evidence_status | Category | Evidence for each entry | Uploaded, Pending, Not required
rule_version | Text | Rule table version applied | RULE-YYYY-NN
journey_stage | Category | Filing progress | File, Pay, Confirm, Certificate