## Overview
MyTicketSeller Event Ticketing Platform
Status | Live
Domain | Event technology and payments
Role | Founder, Product Owner and Business Analyst
Business problem | Organisers selling to Nigerian and diaspora audiences needed to take payment in more than one currency, get paid reliably and control who enters. Early builds were split across separate codebases, payment callbacks were unreliable and revenue was reported in blended currencies.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Released" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Take payment reliably and deliver tickets immediately
OBJ-02 | Report revenue, balances and payouts accurately in each currency
OBJ-03 | Control event access through ticket ownership, team roles and scanning
OBJ-04 | Protect buyers, organisers and the platform through refunds, dispute evidence and security
OBJ-05 | Measure marketing performance only with visitor consent

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Confirmed payments issue tickets in the same checkout session | Must | OBJ-01 | Take payment reliably and deliver tickets immediately | Tickets are emailed once the return page verifies payment; pending orders are reconciled automatically
BR-02 | Revenue, wallet balances and payouts are held and shown per currency | Must | OBJ-02 | Report revenue, balances and payouts accurately in each currency | No figure sums two currencies; each event reports in its own currency
BR-03 | Gateway refunds cancel the ticket and notify the buyer | Must | OBJ-04 | Protect buyers, organisers and the platform through refunds, dispute evidence and security | Webhook signature is verified, the full ticket price is refunded and the ticket shows Cancelled
BR-04 | Organisers grant event access by role | Must | OBJ-03 | Control event access through ticket ownership, team roles and scanning | Door staff, viewer and manager roles exist; scanners can scan only events they own or are invited to
BR-05 | Tickets can be sent, transferred and swapped without distorting revenue | Should | OBJ-03 | Control event access through ticket ownership, team roles and scanning | A swapped ticket moves its revenue and is not counted as a new sale
BR-06 | Chargeback evidence is compiled from checkout records | Should | OBJ-04 | Protect buyers, organisers and the platform through refunds, dispute evidence and security | Terms consent is logged at checkout and an evidence PDF can be exported per dispute
BR-07 | Tracking pixels load only after consent | Must | OBJ-05 | Measure marketing performance only with visitor consent | GA4, Meta and TikTok stay blocked until accepted; purchase events carry an event_id for deduplication
BR-08 | Accounts, content and secrets are protected | Must | OBJ-04 | Protect buyers, organisers and the platform through refunds, dispute evidence and security | Auth endpoints are rate limited, rich text is sanitised and no secret is exposed in code or endpoints

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Return page verifies payment with the gateway before showing tickets | Gateway confirms paid: order completes; the webhook is a backup, not the only path
FR-02 | BR-01 | Scheduled reconciliation re-checks orders left pending | Orders for events already past are not auto-completed
FR-03 | BR-02 | Wallet ledger and withdrawal requests held per currency | Only active events count toward balance; fees shown before withdrawal
FR-04 | BR-02 | Event currency derived from its paid ticket types | A free ticket never sets the event or cart currency
FR-05 | BR-03 | Refund handlers for Stripe and Flutterwave webhooks | Invalid signature rejected; refund equals ticket price, not organiser share
FR-06 | BR-04 | Team invitations with door staff, viewer or manager role | Scan endpoint checks event ownership or active invite
FR-07 | BR-05 | Ticket send, transfer and organiser swap | Guest purchases link to an account on login by matching email
FR-08 | BR-06 | Admin dispute-evidence view with PDF export | Includes terms-consent time, reason code and the buyer's prior orders
FR-09 | BR-07 | Consent banner controls GA4, Meta Pixel and TikTok Pixel | No tracking script loads before consent is recorded
FR-10 | BR-08 | Rate limits on auth, sanitised rich text and security headers | App refuses to start in production without a JWT secret

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | a ticket buyer | my tickets the moment my payment succeeds | I never pay twice because the page said it failed | my card has been charged | I return to the site | my order shows paid and the tickets are in my inbox
US-02 | BR-02 | an organiser selling in naira and pounds | to see earnings in each currency separately | I know exactly what I can withdraw | an event has sales in GBP | I open my wallet | the GBP balance is shown on its own, with fees itemised
US-03 | BR-04 | an organiser | to invite door staff who can only scan my event | I do not have to share my login | I invite a person as door staff | they sign in and scan | they can scan my event and cannot see earnings

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Event organisers | High | High | Payouts, sales visibility, door control | Earnings rules, payout timing | Dashboard messages and release notes | Per release | Manage closely
Ticket buyers | Low | High | Fast checkout, instant tickets, refunds | Order status, refund outcome | Transactional email | Per order | Keep informed
Door and scanning staff | Low | Medium | Simple, fast scanning | Their role and event | Invite email and in-app guidance | Per event | Keep informed
Platform admin and finance | High | High | Accurate revenue, withdrawals, disputes | Currency totals, pending approvals | Admin panel | Daily | Manage closely
Contract developers | High | Medium | Clear, testable requirements | Acceptance criteria and priorities | Backlog walkthrough | Each sprint | Keep satisfied
Payment providers | Medium | Low | Correct integration and dispute handling | Webhook and dispute data | Provider dashboards | As needed | Monitor

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Payment callbacks arrive late or not at all | High | Verify on return page and reconcile pending orders | Product owner
R-02 | Currency errors misstate organiser earnings | High | Per-currency ledger and display rules | Product owner
R-03 | Security gaps left by rapid early builds | High | Audit: remove debug endpoints, move secrets, rate limit auth | Product owner
R-04 | Chargebacks lost without evidence | Medium | Log terms consent and export evidence per dispute | Admin and finance
R-05 | Dependence on individual contract developers | Medium | Single codebase, written requirements and owner-led fixes | Product owner

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a buyer whose payment succeeded but whose webhook is delayed | they land on the return page | the order is verified and tickets are emailed | Released
UAT-02 | BR-01 | an order left pending for a future event | reconciliation runs | a paid order completes and an unpaid one stays pending | Released
UAT-03 | BR-02 | an event with naira and pound sales | the organiser opens the wallet | each currency shows its own balance | Released
UAT-04 | BR-03 | a refund issued in Stripe | the webhook arrives | the ticket is cancelled and the buyer is emailed | Released
UAT-05 | BR-04 | door staff invited to event A | they scan a ticket for event B | the scan is refused | Released
UAT-06 | BR-05 | an organiser swaps a sold ticket | revenue is recalculated | the total is unchanged and no new sale appears | Released
UAT-07 | BR-06 | a chargeback on a completed order | admin exports evidence | the PDF shows consent time, reason code and prior orders | Released
UAT-08 | BR-07 | a first-time visitor | they have not accepted cookies | no GA4, Meta or TikTok request is sent | Released

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01, FR-02 | US-01 | UAT-01, UAT-02
BR-02 |  | FR-03, FR-04 | US-02 | UAT-03
BR-03 |  | FR-05 | None | UAT-04
BR-04 |  | FR-06 | US-03 | UAT-05
BR-05 |  | FR-07 | None | UAT-06
BR-06 |  | FR-08 | None | UAT-07
BR-07 |  | FR-09 | None | UAT-08
BR-08 |  | FR-10 | None | None

## Data Dictionary
Field | Type | Definition | Allowed values
order_id | Text | Unique ticket purchase | Gateway reference plus internal ID
payment_status | Category | State of the purchase | Pending, Completed, Failed, Refunded
currency | Category | Currency of the event and sale | NGN, GBP, USD, EUR and others enabled
ticket_status | Category | State of an issued ticket | Active, Transferred, Cancelled, Scanned
team_role | Category | Access granted to a team member | door_staff, viewer, manager
tos_accepted_at | Datetime | When the buyer accepted the terms | ISO 8601
scan_result | Category | Outcome of a scan | Admitted, Duplicate, Invalid, Not your event