## Overview
The Ecommerce Boss SME Consulting
Status | Ongoing (2024 to present)
Domain | SME digital services: marketing operations and web development
Role | Business Analyst
Business problem | Small-business owners arrive with a solution already in mind, such as a new website or more sales from social media. Underneath there is usually no agreed goal, enquiries scattered across direct messages, forms and spreadsheets, and no way to see what marketing or the website actually returns, all on a tight budget.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Released" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Agree the business goal and success measure before anything is built
OBJ-02 | Deliver websites and tools that fit the business's budget and capacity
OBJ-03 | Capture every enquiry in one traceable record with a clear next step
OBJ-04 | Make marketing and website performance measurable
OBJ-05 | Leave the owner able to run the solution after handover

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Each engagement starts with a discovery brief the owner agrees | Must | OBJ-01 | Agree the business goal and success measure before anything is built | Goal, users, constraints and success measure are written down and signed off before build
BR-02 | Scope is prioritised against the budget | Must | OBJ-02 | Deliver websites and tools that fit the business's budget and capacity | Must items fit the budget; Should, Could and Won't items are recorded with reasons
BR-03 | Enquiries from every channel land in one record | Must | OBJ-03 | Capture every enquiry in one traceable record with a clear next step | Website, form and social enquiries create a record with source, status and owner
BR-04 | Routine follow-ups are automated | Should | OBJ-03 | Capture every enquiry in one traceable record with a clear next step | Confirmations and reminders send without manual copying
BR-05 | Websites and campaigns are measurable, with consent | Must | OBJ-04 | Make marketing and website performance measurable | Key actions are tracked in GA4 and tags load only after consent
BR-06 | Changes are tested with the owner before go-live | Must | OBJ-05 | Leave the owner able to run the solution after handover | Agreed scenarios pass; issues are logged, fixed and retested
BR-07 | Owners can run the solution themselves | Should | OBJ-05 | Leave the owner able to run the solution after handover | A handover guide and walkthrough are completed before sign-off

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Discovery template covering goal, users, current process and constraints | Owner confirms the brief before any estimate
FR-02 | BR-02 | Prioritised backlog with MoSCoW labels and estimates | Running total of Must items cannot exceed the budget
FR-03 | BR-03 | Website and landing-page forms write to one Airtable base | Each record stores source channel, status and owner
FR-04 | BR-03 | Social and messaging enquiries logged through a quick-add form | Duplicate contacts are flagged by email or phone
FR-05 | BR-04 | Make or Zapier scenarios send confirmations and reminders | Failed automations alert the owner
FR-06 | BR-05 | GA4 events on calls to action, forms and purchases | Tracking loads only after cookie consent
FR-07 | BR-06 | UAT checklist run with the owner on staging | No go-live with an open high-severity issue
FR-08 | BR-07 | Handover guide and recorded admin walkthrough | Owner completes one change unaided before sign-off

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | a small-business owner | to agree what success looks like before I pay for a build | I get a website that grows the business, not just a new design | I have asked for a new website | the discovery session ends | I have a written goal, success measure and prioritised scope
US-02 | BR-03 | a business owner | every enquiry in one place with its next step | no lead goes cold in my DMs | an enquiry comes in through Instagram or the website | I open my records | it is there with its source, status and who owns the follow-up
US-03 | BR-05 | a business owner | to see which channels bring customers | I spend my marketing budget on what works | campaigns are running | I review the month | I can see enquiries and sales by source

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Business owners and founders | High | High | Growth, cost and time | Options, costs, progress and results | Discovery workshop and weekly check-ins | Weekly | Manage closely
Client staff (sales, marketing, admin) | Medium | High | Tools that save time | New processes and how to use them | Walkthroughs and handover guides | Per release | Keep informed
Customers of the business | Low | High | Easy buying and quick replies | Journey and communication | Usability checks | Per release | Keep informed
Freelance designers and developers | Medium | Medium | Clear, buildable requirements | Acceptance criteria and priorities | Backlog walkthrough | Each sprint | Keep satisfied
Platform providers | Low | Low | Correct configuration | Integration and account settings | Provider documentation | As needed | Monitor

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Scope grows beyond a fixed small-business budget | High | MoSCoW prioritisation and a change log agreed with the owner | Business analyst
R-02 | Owner has little time for discovery and testing | High | Short, structured sessions and clear decision points | Business analyst
R-03 | Tools are abandoned after handover | Medium | Simple tools, training and a written guide | Business owner
R-04 | Poor data quality in legacy spreadsheets | Medium | Validation at intake and a one-off clean-up | Business analyst
R-05 | Tracking set up without consent | High | Consent-gated tags checked in UAT | Business analyst

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a new engagement | discovery is complete | the owner has signed off goal, measure and scope | Passed
UAT-02 | BR-02 | a backlog over budget | priorities are reviewed | Must items fit the budget and the rest are recorded | Passed
UAT-03 | BR-03 | an enquiry through the website form | it is submitted | a record appears with source, status and owner | Passed
UAT-04 | BR-03 | the same customer enquires twice | the second record is created | it is flagged as a possible duplicate | Passed
UAT-05 | BR-04 | a new enquiry | the automation runs | the customer receives a confirmation | Passed
UAT-06 | BR-05 | a visitor who has not accepted cookies | they browse the site | no analytics tag loads | Passed
UAT-07 | BR-07 | handover is complete | the owner updates a page and a record alone | both changes succeed | Passed

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | US-01 | UAT-01
BR-02 |  | FR-02 | None | UAT-02
BR-03 |  | FR-03, FR-04 | US-02 | UAT-03, UAT-04
BR-04 |  | FR-05 | None | UAT-05
BR-05 |  | FR-06 | US-03 | UAT-06
BR-06 |  | FR-07 | None | None
BR-07 |  | FR-08 | None | UAT-07

## Data Dictionary
Field | Type | Definition | Allowed values
lead_id | Text | Unique enquiry record | Auto-generated ID
source_channel | Category | Where the enquiry came from | Website, Instagram, WhatsApp, Referral, Ads
status | Category | Stage of the enquiry | New, Contacted, Quoted, Won, Lost
owner | Text | Person responsible for the next step | Named staff member
consent_status | Category | Marketing consent given | Granted, Not granted
created_at | Datetime | When the enquiry arrived | ISO 8601