## Overview
NaijaFoodFestival Multi-user Registration Service
Status | Delivered
Domain | Events and hospitality
Role | Product Owner and Business Analyst, HunterTV Africa
Business problem | A single registration concept did not reflect the different information, approval and communication needs of attendees, vendors and volunteers.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Passed" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Separate the three user journeys
OBJ-02 | Reduce incomplete records and manual follow-up
OBJ-03 | Give organisers status and exception visibility
OBJ-04 | Validate end-to-end communications before launch

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Each user group follows a route relevant to its purpose | Must | OBJ-01 |  | Only relevant fields and guidance appear for the chosen route
BR-02 | Submissions cannot be completed with missing mandatory data | Must | OBJ-02 |  | Incomplete submissions are blocked with a clear correction message
BR-03 | Organisers can view every submission status | Must | OBJ-03 |  | Route, status, date and next action are visible for each record
BR-04 | Vendor decisions trigger the correct communication | Must | OBJ-04 |  | Message sent and record status agree
BR-05 | Volunteer allocation uses availability and need | Should | OBJ-03 |  | Allocation is visible to authorised organisers
BR-06 | Attendees receive purchase or registration confirmation | Must | OBJ-04 |  | Confirmation and transaction status are recorded

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Landing page asks the visitor to choose attendee, vendor or volunteer | Choice loads the matching form only
FR-02 | BR-02 | Mandatory fields are validated before submission | Vendor: business name, category, food-safety evidence; Volunteer: availability
FR-03 | BR-03 | Every submission creates a record with route, status, owner and next action | Status values: Submitted, Under review, Approved, Declined, Allocated
FR-04 | BR-04 | Approve or decline action sends the matching template | Message is only sent after the status update succeeds
FR-05 | BR-05 | Volunteer records hold availability slots and allocated role | A volunteer cannot be allocated to overlapping slots
FR-06 | BR-06 | Ticket purchase returns a confirmation email with ticket reference | Failed payments do not generate a ticket

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-01 | vendor | an application that only asks what vendors need | I can apply quickly and correctly | I choose Vendor on the landing page | the form loads | I see vendor fields and guidance only
US-02 | BR-04 | organiser | decision emails sent from the record | vendors never get a message that contradicts our records | a vendor application is under review | I mark it Approved | the status updates and the approval email is sent
US-03 | BR-03 | organiser | one view of all submissions and their next action | nothing is missed before the event | submissions exist across all three routes | I open the status view | each record shows route, status, date and owner

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Event organisers | High | High | Operational control and reporting | Status, exceptions, decisions | Status review and decision log | Twice weekly before launch | Manage closely
Attendees | Low | High | Simple purchase and communication | Ticket and event information | Website content and confirmation email | At purchase and event updates | Keep informed
Vendors | Medium | High | Transparent application and decision | Requirements, decision, next steps | Application guidance and decision email | At application and decision | Keep informed
Volunteers | Low | High | Clear allocation and instructions | Role, shift, briefing | Allocation email and briefing pack | At allocation and event week | Keep informed
Developers and creatives | High | Medium | Agreed journeys, content and rules | Journey maps, field lists, templates | Build brief and review session | Each build cycle | Keep satisfied

## RAID
ID | Risk | Severity | Response | Owner
R-01 | One form collects irrelevant information | High | Separate routes by purpose | Business analyst
R-02 | Email and record status diverge | High | Send only after status update; trigger tests | Developer
R-03 | Vendor approval rules are incomplete | Medium | Decision checkpoint with organisers | Event organiser
R-04 | Ticketing or email service is unavailable | Medium | Fallback communication and manual list | Project manager

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a visitor on the landing page | they choose Volunteer | only volunteer fields and guidance load | Passed
UAT-02 | BR-02 | a vendor leaves food-safety evidence empty | they submit | submission is blocked with a correction message | Passed
UAT-03 | BR-03 | records exist in all three routes | an organiser opens the status view | route, status, date and next action show for each | Passed
UAT-04 | BR-04 | a vendor record under review | the organiser approves it | status changes and the approval email is sent once | Passed
UAT-05 | BR-05 | a volunteer with one availability slot | an organiser allocates two overlapping shifts | the second allocation is rejected | Passed
UAT-06 | BR-06 | an attendee completes payment | the transaction succeeds | confirmation email with ticket reference is received | Passed

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | US-01 | UAT-01
BR-02 |  | FR-02 | None | UAT-02
BR-03 |  | FR-03 | US-03 | UAT-03
BR-04 |  | FR-04 | US-02 | UAT-04
BR-05 |  | FR-05 | None | UAT-05
BR-06 |  | FR-06 | None | UAT-06

## Data Dictionary
Field | Type | Definition | Allowed values
submission_id | Text | Unique application or registration | NFF-0001 format
user_route | Category | Journey chosen | Attendee, Vendor, Volunteer
submission_status | Category | Current workflow status | Submitted, Under review, Approved, Declined, Allocated
decision_by | Text | Organiser who made the decision | Named organiser
confirmation_sent | Boolean | Communication delivery status | True, False
assigned_owner | Text | Responsible organiser | Named organiser