## Overview
CONVVA African SME Commerce Platform
Status | Concept / MVP design
Domain | SME commerce and retail technology
Role | Product Business Analyst
Business problem | Small merchants manage products, stock and orders across social media, messaging and separate tools, creating duplication, overselling and weak fulfilment visibility.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Planned" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Create one product and inventory source
OBJ-02 | Connect selected selling channels
OBJ-03 | Give every order a clear status
OBJ-04 | Make setup usable for SMEs

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Maintain one product and inventory record | Must | OBJ-01 |  | All selected channels use the same source
BR-02 | Publish products to selected channels | Must | OBJ-02 |  | Changes appear on each selected channel
BR-03 | Prevent sale of unavailable stock | Must | OBJ-01 |  | Insufficient stock blocks or flags the order
BR-04 | Every order has status and a next action | Must | OBJ-03 |  | Merchant can identify the next step for each order
BR-05 | Guided setup for payment and delivery providers | Must | OBJ-04 |  | Merchant completes setup without support

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Product record holds variants, price and stock | Stock cannot go below zero
FR-02 | BR-02 | Merchant selects channels per product | Channel sync failure is shown on the product
FR-03 | BR-03 | Order reserves stock for 15 minutes pending payment | Unpaid reservations release automatically
FR-04 | BR-04 | Order timeline shows payment, fulfilment and delivery states | Next action displayed at the top of each order
FR-05 | BR-05 | Setup wizard lists providers available in the merchant country | Test transaction required before go-live

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-03 | merchant | orders to reserve stock automatically | I never sell what I do not have | one item is left | two customers order at once | the second order is told the item is unavailable
US-02 | BR-04 | merchant | one timeline for each order | I know what to do next | an order is paid | I open it | the next action, Accept fulfilment, is shown first

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
SME merchants | Medium | High | Simple operations and sales | Setup, orders, stock | In-app guidance and WhatsApp support | Ongoing | Keep informed
Customers | Low | High | Reliable ordering | Order and delivery status | Notifications | At each status change | Keep informed
Payment providers | High | Medium | Transaction status | API usage, volumes | Partner review | Quarterly | Keep satisfied
Delivery providers | Medium | Medium | Fulfilment data | Pickup and delivery events | Partner integration brief | At onboarding | Monitor
Platform admin | High | High | Support and exception control | Failed syncs, disputes | Admin console | Daily | Manage closely

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Channel stock becomes inconsistent | High | Single inventory source and sync alerts | Product owner
R-02 | Failed payment appears complete | High | Confirmed payment states only | Engineering lead
R-03 | Setup is too complex for merchants | Medium | Guided wizard and usability tests | Business analyst
R-04 | Provider outage blocks fulfilment | Medium | Exception queue and fallback provider | Operations

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | stock changed in the catalogue | channels are checked | all show the new quantity | Planned
UAT-02 | BR-02 | a channel sync fails | the merchant opens the product | the failure and retry option show | Planned
UAT-03 | BR-03 | one item left and two orders | both are placed together | only one reserves stock | Planned
UAT-04 | BR-04 | a paid order | the merchant opens it | next action and timeline show | Planned
UAT-05 | BR-05 | a new merchant | they complete the wizard | a test transaction succeeds without support | Planned

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | None | UAT-01
BR-02 |  | FR-02 | None | UAT-02
BR-03 |  | FR-03 | US-01 | UAT-03
BR-04 |  | FR-04 | US-02 | UAT-04
BR-05 |  | FR-05 | None | UAT-05

## Data Dictionary
Field | Type | Definition | Allowed values
merchant_id | Text | Unique merchant | MER-0001 format
product_id | Text | Unique product | PRD-0001 format
channel | Category | Sales channel | Storefront, Instagram, WhatsApp, Facebook
available_stock | Integer | Sellable quantity | 0 or more
order_status | Category | Order state | Placed, Reserved, Paid, In fulfilment, Delivered, Cancelled
delivery_status | Category | Fulfilment state | Awaiting pickup, In transit, Delivered, Failed