## Overview
IndulgeTix Event Ticketing Platform
Status | Product development
Domain | Event technology and payments
Role | Product Business Analyst
Business problem | Organisers need connected event setup, ticket ownership, scanning and settlement, while attendees need reliable purchase, transfer and refund journeys.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Planned" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Support organisers to configure and publish events
OBJ-02 | Control the ticket lifecycle and ownership
OBJ-03 | Prevent invalid entry at the door
OBJ-04 | Keep money movements reconcilable and auditable

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Organisers can create single, recurring and multi-day events | Must | OBJ-01 |  | Each event type validates its required settings
BR-02 | Each issued ticket has exactly one valid owner state | Must | OBJ-02 |  | Ownership history is retained for every change
BR-03 | Transfer and refund rules are enforced | Must | OBJ-02 |  | Invalid state transitions are rejected with a reason
BR-04 | Scanning prevents duplicate or invalid entry | Must | OBJ-03 |  | A second scan of the same ticket is rejected and flagged
BR-05 | Settlement reconciles tickets, fees and refunds before payout | Must | OBJ-04 |  | Variance is shown before payout is released

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Event wizard captures type, dates, capacity and ticket tiers | Recurring events require an end date or occurrence count
FR-02 | BR-02 | Ticket record holds owner, state and state history | States: Reserved, Issued, Transferred, Refunded, Scanned, Void
FR-03 | BR-03 | Transfer requires recipient acceptance before ownership moves | Scanned or refunded tickets cannot be transferred
FR-04 | BR-03 | Refund eligibility checks organiser policy and event date | Refund voids the ticket before money is returned
FR-05 | BR-04 | Scanner validates ticket state in real time | Valid scan moves ticket to Scanned; repeat scan shows first-scan time
FR-06 | BR-05 | Settlement report totals sales, fees, refunds and chargebacks per event | Payout blocked while variance is not zero or explained

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-03 | attendee | to transfer my ticket to a friend | they can attend in my place | I own an Issued ticket | my friend accepts the transfer | the ticket shows my friend as owner and my copy is void
US-02 | BR-04 | door staff member | a clear result when I scan | I admit only valid tickets quickly | a ticket was already scanned | I scan it again | the scanner shows Rejected with the first-scan time
US-03 | BR-05 | organiser | to see reconciled totals before payout | I trust what I am paid | my event has ended | I open settlement | sales, fees, refunds and variance are shown before I confirm

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Attendees | Low | High | Reliable purchase and access | Ticket, transfer, refund status | In-app notifications | At each ticket event | Keep informed
Organisers | High | High | Control, sales and payout | Sales, capacity, settlement | Dashboard and settlement report | Live and after event | Manage closely
Door staff | Low | High | Fast valid scanning | Scan results, exceptions | Scanner app briefing | Before each event | Keep informed
Finance and compliance | High | Medium | Audit and settlement | Reconciliation, variance | Settlement review | Per payout | Keep satisfied
Affiliate resellers | Medium | Medium | Attribution and commission | Sales by code | Affiliate statement | Weekly | Monitor

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Duplicate ticket ownership | High | State model and audit log | Product owner
R-02 | Duplicate entry | High | Real-time scan validation | Product owner
R-03 | Settlement variance | High | Pre-payout reconciliation | Finance lead
R-04 | Refund or transfer abuse | High | Eligibility and permission rules | Product owner

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | an organiser creates a recurring event | no end date or count is given | publish is blocked with a message | Planned
UAT-02 | BR-02 | a ticket is transferred twice | history is opened | three owners appear in order with timestamps | Planned
UAT-03 | BR-03 | a Scanned ticket | the owner requests a transfer | the request is rejected with a reason | Planned
UAT-04 | BR-04 | a ticket already scanned | it is scanned again | Rejected shows with the first-scan time | Planned
UAT-05 | BR-05 | an event with one unmatched refund | the organiser opens settlement | variance shows and payout is blocked | Planned

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | None | UAT-01
BR-02 |  | FR-02 | None | UAT-02
BR-03 |  | FR-03, FR-04 | US-01 | UAT-03
BR-04 |  | FR-05 | US-02 | UAT-04
BR-05 |  | FR-06 | US-03 | UAT-05

## Data Dictionary
Field | Type | Definition | Allowed values
event_id | Text | Unique event | EVT-0001 format
ticket_id | Text | Unique ticket | Random, non-sequential
owner_id | Text | Current ticket owner | User ID
ticket_state | Category | Lifecycle state | Reserved, Issued, Transferred, Refunded, Scanned, Void
payment_status | Category | Payment state | Pending, Confirmed, Failed, Refunded
scan_timestamp | Datetime | First valid scan | ISO 8601