## Overview
Verdaso ESG Evidence Infrastructure
Status | Concept / MVP design
Domain | ESG, compliance and sustainability technology
Role | Product Business Analyst
Business problem | SMEs hold ESG evidence in photos, PDFs and spreadsheets without source context, so reports are slow to assemble and hard for auditors to trust.
Measure | Value | Source
Business requirements |  | Requirements
Must requirements |  | Requirements
Should requirements |  | Requirements
Functional requirements |  | Functional
Requirements with a test |  | Traceability
Tests with status "Planned" |  | UAT
High risks |  | RAID
Stakeholder groups |  | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Capture source evidence with metadata
OBJ-02 | Keep a human validation step before approval
OBJ-03 | Maintain controlled, auditable records
OBJ-04 | Generate framework-aligned outputs

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Evidence retains source and capture metadata | Must | OBJ-01 |  | Every record links to its original source
BR-02 | AI extraction is reviewed before approval | Must | OBJ-02 |  | Unvalidated content is clearly labelled
BR-03 | Corrections preserve audit history | Must | OBJ-03 |  | Prior and current values remain traceable
BR-04 | Views follow stakeholder permissions | Must | OBJ-03 |  | Unauthorised evidence is never displayed
BR-05 | Reports identify framework and version | Should | OBJ-04 |  | Output records framework name and version

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Capture stores file hash, timestamp and permitted location | Location precision follows the organisation setting
FR-02 | BR-02 | Extracted fields default to Draft until a reviewer approves | Draft values cannot appear in reports
FR-03 | BR-03 | Corrections append a new version with reason | Original values are never overwritten
FR-04 | BR-04 | Role-based views for SME, auditor and investor | Investor view shows approved summary only
FR-05 | BR-05 | Framework mapping tables are effective-dated | Reports print framework and mapping version

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-02 | reviewer | to approve extracted values before they count | AI mistakes never reach a report | a document has been extracted | I approve the values | they become part of the versioned record
US-02 | BR-01 | auditor | to trace any figure back to its source | I can test the evidence | a report figure | I click it | the original file, capture time and approver are shown

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
SME operators | Medium | High | Simple evidence capture | What to capture and when | In-app checklist | Per reporting period | Keep informed
Auditors | High | High | Traceability and validation | Source links, approval trail | Auditor walkthrough | At audit | Manage closely
Investors and buyers | Medium | Medium | Reliable authorised evidence | Approved summaries | Shared report view | Quarterly | Monitor
Framework specialists | High | Medium | Correct mappings | Framework changes | Mapping review | On framework update | Keep satisfied
Data protection and security | High | Medium | Location and document controls | Data flows, retention | DPIA review | Before launch | Keep satisfied

## RAID
ID | Risk | Severity | Response | Owner
R-01 | AI misclassifies evidence | High | Mandatory human validation | Product owner
R-02 | Location data creates privacy risk | High | Purpose limitation and precision control | Data protection lead
R-03 | Immutable record blocks lawful correction | High | Append-only correction model | Product owner
R-04 | Framework requirements change | High | Effective-dated mappings | Framework specialist

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a photo is captured | the record is opened | hash, timestamp and permitted location are shown | Planned
UAT-02 | BR-02 | extracted values in Draft | a report is generated | draft values are excluded and flagged | Planned
UAT-03 | BR-03 | an approved value is corrected | history is viewed | both versions show with reason and approver | Planned
UAT-04 | BR-04 | an investor user | they open raw evidence | access is denied | Planned
UAT-05 | BR-05 | a CSRD report | it is exported | framework and mapping version appear on the output | Planned

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 |  | FR-01 | US-02 | UAT-01
BR-02 |  | FR-02 | US-01 | UAT-02
BR-03 |  | FR-03 | None | UAT-03
BR-04 |  | FR-04 | None | UAT-04
BR-05 |  | FR-05 | None | UAT-05

## Data Dictionary
Field | Type | Definition | Allowed values
evidence_id | Text | Unique evidence record | EVD-0001 format
source_type | Category | Captured format | Photo, PDF, CSV
capture_timestamp | Datetime | Creation time | ISO 8601
location_metadata | Geospatial | Permitted source-proof location | Precision per organisation setting
validation_status | Category | Review state | Draft, Approved, Rejected, Superseded
framework_version | Text | Mapping used | Framework and version code