## Overview
AI Evaluation Quality and Consistent Judgement
Status | Delivered evaluation work
Domain | Artificial intelligence services
Role | AI Evaluation Contractor
Business problem | Evaluating AI outputs at scale needs consistent interpretation of criteria, clear separation of evidence from assumption, and safe adaptation when guidance changes.
Measure | Value | Source
Business requirements | 4 | Requirements
Must requirements | 3 | Requirements
Should requirements | 1 | Requirements
Functional requirements | 4 | Functional
Requirements with a test | 4 | Traceability
Tests with status "Applied in practice" | 4 | UAT
High risks | 4 | RAID
Stakeholder groups | 4 | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Apply the current criteria consistently
OBJ-02 | Separate evidence from assumption
OBJ-03 | Record clear, checkable rationale
OBJ-04 | Adapt safely when guidance changes

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | The active criteria version is visible on every task | Must | OBJ-01 | Apply the current criteria consistently | Each decision links to a guidance version
BR-02 | Each criterion has a recorded assessment | Must | OBJ-02 | Separate evidence from assumption | Required criterion fields cannot be skipped
BR-03 | Rationale cites observed evidence | Must | OBJ-03 | Record clear, checkable rationale | Explanation quotes or points to the specific issue
BR-04 | Ambiguous cases can be escalated | Should | OBJ-04 | Adapt safely when guidance changes | Escalation route and status are visible

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Task view shows the guidance version and change notes | Superseded versions are read-only
FR-02 | BR-02 | Rating form lists factuality, completeness, reasoning and adherence | Submission blocked until every criterion is rated
FR-03 | BR-03 | Rationale field requires an evidence reference | Flags: hallucination, contradiction, missing requirement
FR-04 | BR-04 | Escalate button routes the case to the guidance owner | Escalated tasks pause until answered

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-03 | quality reviewer | rationales that point to specific evidence | I can verify a decision quickly | an evaluator flags a hallucination | they submit | the rationale shows the exact claim and why it is unsupported

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Evaluation client | High | Medium | Reliable quality decisions | Agreement and quality trends | Quality report | Per batch | Keep satisfied
Evaluators | Low | High | Clear criteria and examples | Guidance, examples, feedback | Guidance hub and feedback | Each task | Keep informed
Quality reviewers | Medium | High | Consistency evidence | Sampled decisions | Review queue | Daily | Keep informed
Guidance owners | High | High | Controlled updates | Escalations, drift | Escalation channel | As raised | Manage closely

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Criteria interpreted inconsistently | High | Worked examples and calibration | Guidance owner
R-02 | Guidance changes midstream | High | Version control and change notes | Guidance owner
R-03 | Unsupported assumption affects rating | High | Evidence checklist | Evaluator
R-04 | Sensitive content exposed | High | Confidentiality controls | Platform operations

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | guidance v3 is active | a task opens | v3 and its change notes are shown | Applied in practice
UAT-02 | BR-02 | reasoning is not rated | the evaluator submits | submission is blocked | Applied in practice
UAT-03 | BR-03 | a contradiction is found | the rationale is written | it cites the conflicting statements | Applied in practice
UAT-04 | BR-04 | an ambiguous case | it is escalated | the task pauses and shows escalation status | Applied in practice

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 | OBJ-01 | FR-01 | None | UAT-01 | 1
BR-02 | OBJ-02 | FR-02 | None | UAT-02 | 1
BR-03 | OBJ-03 | FR-03 | US-01 | UAT-03 | 1
BR-04 | OBJ-04 | FR-04 | None | UAT-04 | 1

## Data Dictionary
Field | Type | Definition | Allowed values
task_id | Text | Controlled task identifier | Platform ID
criteria_version | Text | Guidance version applied | vN
criterion | Category | Evaluation dimension | Factuality, Completeness, Reasoning, Adherence
rating | Category | Permitted decision | Per rubric scale
rationale | Text | Evidence-based explanation | Must cite evidence
quality_status | Category | Review state | Not sampled, Agreed, Disagreed