## Overview
Healthcare Facilities Request Handling
Status | Generalised operational analysis
Domain | Healthcare support services
Role | Facilities and quality support
Business problem | Facilities requests in a healthcare setting can arrive without impact context, stall on access or resource constraints, and recur without anyone seeing the pattern.
Measure | Value | Source
Business requirements | 5 | Requirements
Must requirements | 3 | Requirements
Should requirements | 2 | Requirements
Functional requirements | 5 | Functional
Requirements with a test | 5 | Traceability
Tests with status "Not applicable (analysis only)" | 5 | UAT
High risks | 2 | RAID
Stakeholder groups | 4 | Stakeholders
Counts are formulas and update when rows are added. Status values are recorded on the UAT sheet.

## Objectives
Objective ID | Objective
OBJ-01 | Record service requests accurately
OBJ-02 | Prioritise by safety impact and urgency
OBJ-03 | Escalate constraints through a named route
OBJ-04 | Use recurrence evidence for corrective action

## Requirements
ID | Requirement | Priority | Objective ID | Objective | Acceptance criterion
BR-01 | Requests record location, timing and impact | Must | OBJ-01 | Record service requests accurately | Required facts are present before work is assigned
BR-02 | Safety and infection risks are prioritised immediately | Must | OBJ-02 | Prioritise by safety impact and urgency | High-risk requests are escalated at intake
BR-03 | Access and resource constraints have a named owner | Must | OBJ-03 | Escalate constraints through a named route | Escalation owner and status are visible
BR-04 | Closure evidence is retained | Should | OBJ-01 | Record service requests accurately | Closure is recorded consistently
BR-05 | Recurring issues can be identified | Should | OBJ-04 | Use recurrence evidence for corrective action | Records can be grouped by type and location

## Functional
ID | Parent BR | System behaviour | Business rule or validation
FR-01 | BR-01 | Intake captures location, time, issue type and impact | Submission blocked if impact is missing
FR-02 | BR-02 | Safety or infection flag sets top priority | Flagged requests notify the supervisor
FR-03 | BR-03 | Escalation records owner, constraint and target date | Open escalations listed by age
FR-04 | BR-04 | Closure requires completion note | Closed requests cannot be edited
FR-05 | BR-05 | Monthly view groups requests by type and location | Three or more repeats flag a pattern

## User Stories
ID | Parent BR | As a | I want | So that | Given | When | Then
US-01 | BR-05 | supervisor | to see repeat issues by location | I can fix causes, not symptoms | a month of closed requests | I open the recurrence view | locations with three or more repeats are flagged

## Stakeholders
Stakeholder | Influence | Interest | Primary interest | Information need | Method | Cadence | Approach
Clinical colleagues | Medium | High | Safe uninterrupted service | Status of their request | Request acknowledgement | Per request | Keep informed
Facilities team | Medium | High | Clear requests and priorities | Assigned work, priorities | Shift handover | Each shift | Keep informed
Supervisors | High | High | Evidence and resource decisions | Escalations, patterns | Escalation list and monthly review | Daily and monthly | Manage closely
Quality and audit | High | Medium | Compliance and recurrence | Trends, closure evidence | Monthly quality report | Monthly | Keep satisfied

## RAID
ID | Risk | Severity | Response | Owner
R-01 | Urgent issue misprioritised | High | Impact criteria and safety flag | Supervisor
R-02 | Record lacks evidence | Medium | Required intake fields | Facilities lead
R-03 | Sensitive information disclosed | High | No patient data in requests | Supervisor
R-04 | Recurring issue stays local | Medium | Monthly recurrence review | Quality lead

## UAT
Test ID | Requirement | Given | When | Then | Status
UAT-01 | BR-01 | a request without impact | it is submitted | submission is blocked | Not applicable (analysis only)
UAT-02 | BR-02 | an infection-risk request | it is submitted | it is top priority and the supervisor is notified | Not applicable (analysis only)
UAT-03 | BR-03 | an access constraint | it is escalated | owner and target date are recorded | Not applicable (analysis only)
UAT-04 | BR-04 | a completed task | it is closed | a completion note is required | Not applicable (analysis only)
UAT-05 | BR-05 | three repeats in one location | the monthly view opens | the location is flagged | Not applicable (analysis only)

## Traceability
Requirement | Objective ID | Functional requirements | User stories | Test IDs | Number of tests
BR-01 | OBJ-01 | FR-01 | None | UAT-01 | 1
BR-02 | OBJ-02 | FR-02 | None | UAT-02 | 1
BR-03 | OBJ-03 | FR-03 | None | UAT-03 | 1
BR-04 | OBJ-01 | FR-04 | None | UAT-04 | 1
BR-05 | OBJ-04 | FR-05 | US-01 | UAT-05 | 1

## Data Dictionary
Field | Type | Definition | Allowed values
request_id | Text | Unique service request | REQ-0001 format
issue_type | Category | Operational issue class | Cleaning, Waste, Access, Supplies, Other
location | Text | Service location | Area code only
reported_at | Datetime | Request time | ISO 8601
priority | Category | Impact and urgency | Immediate, High, Routine
status | Category | Request state | Open, Escalated, Closed